|  |  |  |  |
| --- | --- | --- | --- |
| Eco-Schools Topic 1  Marine | Action(s):  To draft an eco policy to reduce/eliminate single use plastic across the school.  To create mural or sculpture to highlight harm caused by single use plastic. | How long will it take?  Have policy approved Autumn 1 term.  On-going – for completion by year end | How will we monitor progress?  Eco policy  Draw up mid term plan for each year group to do project – review half termly |
| Aim: To raise awareness of eco issues around marine environment | Who is responsible?  Eco leader  Eco leader/Art Lead | Evaluation:  Eco policy on school website –approved by Governors  Photo evidence |
| Eco-Schools Topic 2  Litter | Action(s):  Each class to be timetabled to do litter picking during Keep Britain Tidy’s Big School Clean.  To have a rota/timetable to tidy St Stephens Church | How long will it take?  To be completed in March during Big School Clean | How will we monitor progress?  luggage scales to weigh litter collected and count entries for competition |
| Aim:  To improve school environment with focus on litter. | Who is responsible?  Eco Committee – choosing poster competition winners  Eco lead – scheduling litter picks  Class Teacher - supervising | Evaluation:  Photo evidence – winner and school ground before and after litter clean |
| Eco-Schools Topic 3  Waste | Action(s):  ~~Record how much paper/books school orders at Autumn 1, monitor through stationery order how much is ordered through year.~~  Ordered several recycling bins which are collected and food waste  Share recycling tips on school website. | How long will it take?  Ongoing  Autumn 1 | How will we monitor progress?  ~~Keep record of paper order~~  Monitor number of bins collected |
| Aim:  To actively reduce waste – ~~focussing on paper~~.  focussing on food | Who is responsible?  Eco lead | Evaluation:  Has paper consumption reduced?  Record visitors to recycling page or similar |